## Slide 1: Test Management

## Slide 2: Learning Objectives
  Responsibilities of a Test Lead and Tester
  Test Planning and Estimation
    Test Planning – Activities
    Entry criteria, Exit criteria
    Test Estimation
    Test Strategy, Approach
  Test Progress Monitoring and Control
  Configuration Management

## Slide 3: Responsibilities of Test Lead
  Co-ordinate the test strategy and plan with project managers and others.
  Write or review a test strategy for the project, and test policy for the organization.
  Contribute the testing perspective to other project activities, such as integration planning.
  Plan the tests –Considering the context and understanding the test objectives and risks –including selecting test approaches, estimating the time, effort and cost of testing, acquiring resources, defining test levels, cycles, and planning incident management.
  Initiate the specification, preparation, implementation and execution of tests, monitor the test results and check the exit criteria.
  Adapt planning based on test results and progress (sometimes documented in status reports) and take any action necessary to compensate for problems.

## Slide 4: Contd..
  Set up adequate configuration management of testware for traceability.
  Introduce suitable metrics for measuring test progress and evaluating the quality of the testing and the product.
  Decide what should be automated, to what degree, and how.
  Select tools to support testing and organize any training in tool use for testers.
  Decide about the implementation of the test environment.
  Write test summary reports based on the information gathered during testing.

## Slide 5: Responsibilities of Tester
  Review and contribute to test plans.
  Analyze, review and assess user requirements, specifications and models for testability.
  Create test specifications.
  Set up the test environment (often coordinating with system administration and network management).
  Prepare and acquire test data.
  Implement tests on all test levels, execute and log the tests, evaluate the results and document the deviations from expected results.
  Use test administration or management tools and test monitoring tools as required.
  Automate tests (may be supported by a developer or a test automation expert).
  Measure performance of components and systems (if applicable).
  Review tests developed by others.

## Slide 6: Test Planning & Estimation

## Slide 7: Test Planning
Test Plan:
Master Test Plan:
Test Planning:
Test planning is a continuous activity and is performed in all life cycle processes and activities.
Planning may be documented in a master test plan and in separate test plans for test levels such as system testing and acceptance testing.
Planning is influenced by the test policy of the organization, the scope of testing, objectives, risks, constraints, criticality, testability and the availability of resources.
A document describing the scope, approach, resources and schedule of intended test activities. It identifies amongst others test items, the features to be tested, the testing tasks, who will do each task, degree of tester independence, the test environment, the test design techniques and entry and exit criteria to be used, and the rationale for their choice, and any risks requiring contingency planning. It is a record of the test planning process. [After IEEE 829]
A test plan that typically addresses multiple test levels.
The activity of establishing or updating a test plan.

## Slide 8: Test Planning Activities
  Determining the scope and risks and identifying the objectives of testing.
  Defining the overall approach of testing, including the definition of the test levels and entry and exit criteria.
  Integrating and coordinating the testing activities into the software life cycle activities (acquisition, supply, development, operation and maintenance).
  Making decisions about what to test, what roles will perform the test activities, how the test activities should be done, and how the test results will be evaluated.
  Scheduling test analysis and design activities.
  Scheduling test implementation, execution and evaluation.
  Assigning resources for the different activities defined.
  Defining the amount, level of detail, structure and templates for the test documentation.
  Selecting metrics for monitoring and controlling test preparation and execution, defect resolution and risk issues.
  Setting the level of detail for test procedures in order to provide enough information to support reproducible test preparation and execution.

## Slide 9: Entry Criteria & Exit Criteria
  Entry criteria define when to start testing such as at the beginning of a test level or when a set of tests is ready for execution.
    Typically entry criteria may cover the following:
      Test environment availability and readiness.
      Test tool readiness in the test environment.
      Testable code availability.
      Test data availability.
  Exit criteria define when to stop testing such as at the end of a test level or when a set of tests has achieved specific goal.
    Typically exit criteria may cover the following:
      Thoroughness measures, such as coverage of code, functionality or risk.
      Estimates of defect density or reliability measures.
      Cost.
      Residual risks, such as defects not fixed or lack of test coverage in certain areas.
      Schedules such as those based on time to market.

## Slide 10: Test Estimation
  Test Estimation:
    The calculated approximation of a result related to various aspects of testing (e.g. effort spent, completion date, costs involved, number of test cases, etc.) which is usable even if input data may be incomplete, uncertain, or noisy.
  Two approaches for the estimation of test effort are:
    The metrics-based approach: Estimating the testing effort based on metrics of former or similar projects or based on typical values.
    The expert-based approach: Estimating the tasks based on estimates made by the owner of the tasks or by experts.
  Once the test effort is estimated, resources can be identified and a schedule can be drawn up.

## Slide 11: Contd..
  The testing effort may depend on a number of factors, including:
    Characteristics of the product:
      The quality of the specification and other information used for test models (i.e. the test basis), the size of the product, the complexity of the problem domain, the requirements for reliability and security, and the requirements for documentation.
    Characteristics of the development process:
      The stability of the organization, tools used, test process, skills of the people involved, and time pressure.
    The outcome of testing:
      The number of defects and the amount of rework required.

## Slide 12: Test Strategy, Test Approach
  Test Strategy:
    A high-level description of the test levels to be performed and the testing within those levels for an organization or programme (one or more projects).
  Test Approach:
    The implementation of the test strategy for a specific project. It typically includes the decisions made that follow based on the (test) project’s goal and the risk assessment carried out, starting points regarding the test process, the test design techniques to be applied, exit criteria and test types to be performed.
  Typical approaches include:
    Analytical approaches, such as risk-based testing where testing is directed to areas of greatest risk
    Model-based approaches, such as stochastic testing using statistical information about failure rates (such as reliability growth models) or usage (such as operational profiles).

## Slide 13: Contd..
  Methodical approaches, such as failure-based (including error guessing and fault-attacks), experienced-based, check-list based, and quality characteristic based.
  Process- or standard-compliant approaches, such as those specified by industry-specific standards or the various agile methodologies.
  Dynamic and heuristic approaches, such as exploratory testing where testing is more reactive to events than pre-planned, and where execution and evaluation are concurrent tasks.
  Consultative approaches, such as those where test coverage is driven primarily by the advice and guidance of technology and/or business domain experts outside the test team.
  Regression-averse approaches, such as those that include reuse of existing test material, extensive automation of functional regression tests, and standard test suites.
  The selection of approach depends on the context and may consider risks, hazards and safety, available resources and skills, the technology, the nature of the system, test objectives and regulations.

## Slide 14: Test Progress Monitoring & Control

## Slide 15: Test Progress Monitoring
  Test Monitoring: A test management task that deals with the activities related to periodically checking the status of a test project. Reports are prepared that compare the actuals to that which was planned.
  The purpose of test monitoring is to provide feedback and visibility about test activities.
  Metrics also used to assess progress against the planned schedule and budget.
  Common test metrics include:
    Percentage of work done in test case preparation (or percentage of planned test cases prepared).
    Percentage of work done in test environment preparation.
    Test case execution (e.g. number of test cases run/not run, and test cases passed/failed).
    Defect information (e.g. defect density, defects found and fixed, failure rate, and re-test results).
    Test coverage of requirements, risks or code.
    Subjective confidence of testers in the product.
    Dates of test milestones.
    Testing costs, including the cost compared to the benefit of finding the next defect or to run the next test.

## Slide 16: Test Reporting
Test reporting is concerned with summarizing information about the testing endeavor, including..
What happened during a period of testing, such as dates when exit criteria were met.
Analyzed information and metrics to support recommendations and decisions about future actions, such as an assessment of defects remaining, the economic benefit of continued testing, outstanding risks, and the level of confidence in the tested software.
Metrics should be collected during and at the end of a test level in order to assess:
The adequacy of the test objectives for that test level.
The adequacy of the test approaches taken.
The effectiveness of the testing with respect to the objectives.

## Slide 17: Test Control
  Test Control: A test management task that deals with developing and applying a set of corrective actions to get a test project on track when monitoring shows a deviation from what was planned.
  Test control describes any guiding or corrective actions taken as a result of information and metrics gathered and reported.
  Actions may cover any test activity and may affect any other software life cycle activity or task.
  Examples of test control actions are:
    Making decisions based on information from test monitoring.
    Re-prioritize tests when an identified risk occurs (e.g. software delivered late).
    Change the test schedule due to availability or unavailability of a test environment.
    Setting an entry criterion requiring fixes to have been re-tested by a developer before accepting them into a build.

## Slide 18: Configuration Management
  Configuration Management: A discipline applying technical and administrative direction and surveillance to: identify and document the functional and physical characteristics of a configuration item, control changes to those characteristics, record and report change processing and implementation status, and verify compliance with specified requirements. [IEEE 610]
  The purpose of configuration management is to establish and maintain the integrity of the products (components, data and documentation) of the software or system through the project and product life cycle.
  For testing, configuration management may involve ensuring that:
    All items of testware are identified, version controlled, tracked for changes, related to each other and related to development items (test objects) so that traceability can be maintained throughout the test process.
    All identified documents and software items are referenced unambiguously in test documentation
  For the tester, configuration management helps to uniquely identify (and to reproduce) the tested item, test documents, the tests and the test harness.
  During test planning, the configuration management procedures and infrastructure (tools) should be chosen, documented and implemented.

## Slide 19: Thank you